## Project List
EXHIBIT RMP___(CAT-4.3): MERCURY AND AIR TOXICS STANDARDS PROJECTS
Environmental Regulations and Requirements for Installing Control Equipment
Proj | WBS Element | Project/WBS Short Text | Plant/Unit | Status | Tech. Screening | APR | NTP | In-Service | Underlying State and Federal Regulations | State Issued Permit, Construction Permit or Approval Order | Compliance Dates
Wyoming Projects
1 | 10002178 | DJ U1 Clean Air - Hg (ACI) | Dave Johnston 1 | In Development | DJ2 baseline testing in Oct. 2010 - results applicable | 10002178 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
2 | 10002178 | DJ U2 Clean Air - Hg (ACI) | Dave Johnston 2 | In Development | DJ2 baseline testing in Oct. 2010 | 10002178 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
3 | 10002180 | DJ U3 Clean Air - Hg (ACI/Ox) | Dave Johnston 3 | In Development | DJ3 baseline testing in Mar. 2011 | 10002180 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
4 | 10002181 | DJ U4 Clean Air - Hg (ACI/Ox) | Dave Johnston 4 | In Development | DJ3 baseline testing in Mar. 2011 - results applicable | 10002181 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
5 | 10003392 | JB U1 Clean Air - Hg (Ox/FGD Add) | Jim Bridger 1 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003392 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
6 | 10003393 | JB U2 Clean Air - Hg (Ox/FGD Add) | Jim Bridger 2 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 | 10003393 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
7 | 10003394 | JB U3 Clean Air - Hg (Ox/FGD Add) | Jim Bridger 3 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003394 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
8 | 10003395 | JB U4 Clean Air - Hg (Ox/FGD Add) | Jim Bridger 4 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003395 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
9 | 10003749 | NT U1 Clean Air - Hg (Ox/FGD Add) | Naughton 1 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003749 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
10 | 10003750 | NT U2 Clean Air - Hg (Ox/FGD Add) | Naughton 2 | In Development | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003750 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
11 | 10003751 | NT U3 Clean Air - Hg (ACI/Ox) | Naughton 3 | Suspended | JB2 baseline testing in Nov. 2010 - additional tests in Oct. 2011 - results applicable | 10003751 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
12 | 10004048 | WY Clean Air - Hg (ACI/Ox) | Wyodak | In Development | DJ3 baseline testing in Mar. 2011 - results applicable | 10004048 | TBD | Apr. 15 | Fed: 40 CFR Part 63 | N/A | TBD
Utah Projects
13 | 10001846 | CB U1 Clean Air - Hg (ACI) | Carbon 1 | In Development | No testing or screening scheduled - State rule does not apply due to Unit 1 size | 10001846 | TBD | Fed: Apr. 15 | Fed: 40 CFR Part 63 State: R307-424 | N/A | TBD
14 | 10001847 | CB U2 Clean Air - Hg (ACI) | Carbon 2 | In Development | No testing or screening scheduled - State rule does not apply due to Unit 2 size | 10001847 | TBD | Fed: Apr. 15 | Fed: 40 CFR Part 63 State: R307-424 | N/A | TBD
15 | 10002887 | HTR U1 Clean Air - Hg (ACI/Ox) | Hunter 1 | In Development | No testing or screening scheduled - results with baghouse indicate no additional controls required | 10002887 | TBD | Fed: Apr. 15 State: Under Review | Fed: 40 CFR Part 63 State: R307-424 | N/A | State: Jan. 2013
16 | 10002888 | HTR U2 Clean Air - Hg (Ox) | Hunter 2 | In Development | No testing or screening scheduled - results with baghouse indicate no additional controls required | 10002888 | TBD | Fed: Apr. 15 State: Under Review | Fed: 40 CFR Part 63 State: R307-424 | N/A | State: Jan. 2013
17 | 10002889 | HTR U3 Clean Air - Hg (Ox) | Hunter 3 | In Development | No testing or screening scheduled - results with baghouse indicate no additional controls required | 10002889 | TBD | Fed: Apr. 15 State: Under Review | Fed: 40 CFR Part 63 State: R307-424 | N/A | State: Jan. 2013
18 | 10002668 | HTG U1 Clean Air - Hg (Ox) | Huntington 1 | In Development | No testing or screening scheduled - results with baghouse indicate no additional controls required | 10002668 | TBD | Fed: Apr. 15 State: Under Review | Fed: 40 CFR Part 63 State: R307-424 | N/A | State: Jan. 2013
19 | 10002669 | HTG U2 Clean Air - Hg (Ox) | Huntington 2 | In Development | No testing or screening scheduled - results with baghouse indicate no additional controls required | 10002669 | TBD | Fed: Apr. 15 State: Under Review | Fed: 40 CFR Part 63 State: R307-424 | N/A | State: Jan. 2013