## Conv NG Schedule
Exhibit CAT - 6: Naughton Unit 3 Natural Gas Conversion Schedule
| Q1-2009 | Q2-2009 | Q3-2009 | Q4-2009 | Q1-2010 | Q2-2010 | Q3-2010 | Q4-2010 | Q1-2011 | Q2-2011 | Q3-2011 | Q4-2011 | Q1-2012 | Q2-2012 | Q3-2012 | Q4-2012 | Q1-2013 | Q2-2013 | Q3-2013 | Q4-2013 | Q1-2014 | Q2-2014 | Q3-2014 | Q4-2014 | Q1-2015 | Q2-2015 | Q3-2015 | Q4-2015 | Q1-2016 | Q2-2016 | Q3-2016 | Q4-2016 | Q1-2017 | Q2-2017 | Q3-2017 | Q4-2017 | Q1-2018 | Q2-2018 | Q3-2018 | Q4-2018
SCR and Baghouse Project Development
SCR and baghouse design basis studies
Develop EPC contract technical specification and RFP package
Bid EPC contract
Regulatory proceedings
EPC contract negotiations
Obtain DEQ Construction permit
SCR and Baghouse Project Implementation
EPC Contract execution (LNTP period only)
EPC contract suspension
EPC contract cancellation for convenience
Natural Gas Conversion Project Development
Technical studies
Develop EPC contract technical specification and RFP package
Obtain DEQ construction permit
Bid EPC contract
EPC contract negotiations
Prepare natural gas supply contract RFP
Bid natural gas supply contract
Natural gas supply contract negotiations
Natural Gas Conversion Project Implementation (2015 Early Date)
Unit discontinues coal fueling
EPC contract execution
EPC contract construction period
Natural gas supply contract execution
Natural gas supply contract construction period
Natural gas supply tie-in
Tie-in outage
Mechanical Completion
Substantial Completion
Final Completion
Natural Gas Conversion Project Implementation (2018 Late Date)
Unit discontinues coal-fueling
Expected EPA final action on WY RH SIP
Refresh bids EPC contract
Refresh EPC contract negotations
EPC contract execution
EPC contract construction period
Refresh bids natural gas supply contract
Refresh natural gas supply contract negotations
Natural gas supply contract execution
Natural gas supply contract construction period
Natural gas supply tie-in
Tie-in outage
Mechanical Completion
Substantial Completion
Final Completion
Assumed natural gas conversion "early" operating date
SCR and baghouse compliance date
Assumed natural gas conversion "late" operating date