## 1 of 7
2014 Feeder Line Replacement Budget
| (A) | (B)
| Feeder Line | Projected 2014 Cost
1 | FL6 1/ | 38750000
2 | FL18 | 2000000
3 | FL34 2/ | 3000000
4 | FL36 Continuation 3/ | 8000000
5 | FL21-50 Continuation 4/ | 250000
6 | Pre-engineering (Future Projects) | 3000000
7 | Total High Pressure | 55000000
1/ The cost shown in column B represents the estimated 2014 cost only. An updated budget for remaining costs in 2015 will be provided on November 15, 2014 as part of the 2015 annual budget.
2/ The FL34 cost shown here represents a small portion of 600 ft. of the anticipated 85,221 ft. replacement of FL34 to occur in 2019. This small portion was moved ahead of schedule to accommodate West Jordan City projects taking place in 2014. The remainder of the FL34 replacement will remain scheduled for 2019.
3/ This is a continuation of the FL36 replacement project that began in 2013.
4/ This is a continuation of the FL21-50 replacement project that began in 2013.
Note: In the Nov 15, 2012 budget file, Feeder Line 21-5 had been scheduled for 2014 , however this project has now been rescheduled to a later year due to schedule variation in other projects.

## 2 of 7
2014 Feederline Replacement Footages
Specific vintages from which pipe will be retired and replaced in 2014 are shown in yellow.
Existing Footages | 1929 | 1943 | 1946 | 1948 | 1949 | 1953 | 1954 | 1955 | 1957 | 1958 | 1959 | 1960 | 1962 | 1963 | 1964 | 1965 | 1966 | 1967 | Retirement/Replacement Footages
FL6 | 0 | 0 | 0 | 70965.5 | 0 | 195 | 149 | 0 | 0 | 42 | 103 | 121 | 0 | 108 | 72 | 0 | 213 | 0
1.05 | [6 empty] | 8 | [9 empty] | 43
1.315 | [10 empty] | 10 | 2
2.375 | [5 empty] | 6
4.5 | [5 empty] | 189 | 141 |  |  |  | 93 | 60 |  | 5 | 9 |  | 170
6.625 | [11 empty] | 59 |  | 103 | 63
8.625
10.75 |  |  |  | 70965.5 | [5 empty] | 42 | [8 empty] | 53000
12.75
FL18 | 2326 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.05
2.375
4.5
6.625
8.625
10.75 | 2326 | [6 empty] | 71 | [10 empty] | 2397
12.75
14 | [7 empty] | 46 | [10 empty] | 46
FL21-50 | 0 | 0 | 0 | 107 | 1479 | 0 | 0 | 0 | 99096 | 0 | 0 | 0 | 0 | 78 | 13528 | 1145 | 325 | 0
2.375
3.5
4.5 |  |  |  | 107 | [10 empty] | 338 | 1 | 2
6.625 |  |  |  |  | 1479 | [10 empty] | 1144 | 323
8.625
20 | [8 empty] | 99096 |  |  |  |  | 78 | 13190 |  |  |  | 1980
FL34 | 0 | 36 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84908.5 | 6 | 242 | 0 | 0 | 16
1.05
1.315 | [12 empty] | 14
2.375
3.5 | [12 empty] | 3
4.5 |  | 36 | 12 | [9 empty] | 168 | 6 | 34
6.625 | [12 empty] | 38.5
8.625
10.75 | [12 empty] | 4
12.75
16 | [12 empty] | 45
20 | [12 empty] | 84636 |  | 208 |  |  | 16 | 600
24
FL36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18221 | 25 | 69 | 175
1.05 | [15 empty] | 5
2.375
3.5
4.5
6.625 | [14 empty] | 18 |  |  |  | 18
8.625 | [14 empty] | 18203 | 20 | 69 | 175 | 18467
12.75
[18 empty] | Total | 76508
Questar Gas Company
Docket 13-057-18
Exhibit 1
Page 2 of 7

## 3 of 7 (06)
FL6: 33 South to Utah County

## 4 of 7 (18)
FL18: Hill Air Force Base

## 5 of 7 (34)
FL34: Salt Lake County I-15 crossing

## 6 of 7 (36)
FL36: South Jordan

## 7 of 7 (21-50)
FL21-50: Clearfield