## 1 of 1
Budget Update
| A | B |  | C | D
| Feeder Line | 2015 Budget |  | Actual Costs to Date | Difference
High Pressure
1 | FL6 | 13000000 | 1/ | 15262345.75 | -2262345.75 | 3/
2 | FL24 | 32466656.14 |  | 31805124.64 | 661531.5
3 | FL34 | 3000000 |  | 339778.56 | 2660221.44 | 4/
4 | FL26 | 3300000 |  | 6433745.2 | -3133745.2 | 5/
5 | Total High Pressure | 51766656.14 |  | 53840994.15 | -2074338.01
Intermediate High Pressure
6 | Salt Lake County Total | 6960000 |  | 6581644.27 | 378355.73
7 | Weber County Total | 2650000 |  | 5049689.86 | -2399689.86 | 6/
| Total Intermediate High Pressure | 9610000 |  | 11631334.13 | -2021334.13
8 | Pre-engineering (Future Projects) | 1490000 |  | 952707.39 | 537292.61
9 | Total Annual Budget | 62866656.14 | 2/ | 66425035.67 | -3558379.53
1/ | As indicated in the April 2015 technical conference, the 2015 budget for FL6 is 13MM.
2/ | Reflects allowed 2015 spending amount of $66,100,000 ($65MM + inflation) less $3,233,344 already spent in 2014. See 2014 Fourth Quarter Variance Report filed in Docket No. 13-057-18 dated March 19, 2015.
3/ | The Company encountered unanticipated costs related to a property condemnation, an unanticipated route through a neighborhood that required work in yards instead of the street, and complicated negotiations with Draper City which increased time and related costs.
4/ | Scope was reduced.
5/ | The Company incurred costs related to a property condemnation and a directional drill that was deeper than planned due to the geography in the area.
6/ | The Company expanded the scope of work in Weber County to accomodate a city road project.