## List
Attachment 1B - Project Document Deliverables
Project Description: | [9 empty] | Project Manager:
Plant: | [9 empty] | Plant Project Team:
Unit No.: | [9 empty] | Project Start Date:
WBS No.: | [9 empty] | Project End Date:
No. of Hard Copies | No. of Electronic Copies | COMPANY: Plant to provide EXAMPLE | COMPANY: Corporate to provide EXAMPLE | Required | STAGE |  |  | Deliverable |  |  | Description | Company Submittal Schedule | Contractor Proposed Submittal Schedule | Submittal Folder / Disc(s) | Review
[5 empty] | Review | Construction | As-Built/As-Installed | Use filtering buttons below to narrow down the list of items you need to look through by group | [6 empty] | Comment (1st Issue) | Construction Rev 0 | Construction Rev 1 | Construction Rev 2 | Construction Rev 3 | As Built / Record
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Billing and payment procedures | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Communications plan | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Compliance and understanding agreement to Company drawing and documentation standards See Attachment 1A | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Document control, project filing system, distribution and action tracking (including sub-contractors) See Attachment 1A | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Drawing and document numbering scheme- see Attachment 1A | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Engineering procedures | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Minutes of meetings records and follow up procedure | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Notice of termination | 1D |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Procedure for design, review, comment and approvals |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Procedure for professional engineer sealing of drawings | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Procurement specification, procedures and log | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Progress report plan | 8AA plan / reports monthly |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Project organization with individuals areas of responsibility and contact information | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Punch list and close out plan |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | Scheduling plan to include engineering, procurement, construction and integrated path schedule | 8AA plan / reports monthly |  | Non-drawing
|  |  |  | X |  |  |  | Project | Management and Control Procedures | 1 | System list and equipment numbering schemes - see Attachment 1A | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | All performance guarantee test plans and procedures including correction curves | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | As-builds policy and procedure | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Calibration of instruments policy and procedure | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Constructability reviews | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Construction permits | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Electrical test programs and acceptance test procedures | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Erection specifications | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Field changes policy and procedure | 8AAplan / ?D report |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Inspections policy and procedure | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Installation specifications | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Notice of intent | 10DBF |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Punch list and close out policy and procedure | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Reference to contract statement of work | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Reporting non-conformance policy and procedure | 8AAplan / ?D report |  | Non-drawing
|  |  |  | X |  |  |  | Construction | Plan and Procedures | 2 | Testing requirements / policy and procedure (including performance guarantee test plans) | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start up organization chart |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up administrative procedure |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up safety clearance procedure |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up schedule- Primavera and Microsoft Project |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up test procedures for each mechanical completion, performance and equipment demonstration test items |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up turn over sequences and procedures |  |  | Non-drawing
|  |  |  | X |  |  |  | Start-Up | Plan and Procedures | 3 | Start-up work responsibility matrix |  |  | Non-drawing
|  |  |  | X |  |  |  | Safety | Plan and Procedures | 4 | Construction safety reports |  |  | Non-drawing
|  |  |  | X |  |  |  | Safety | Plan and Procedures | 4 | Hot Work Permit | ?DBF |  | Non-drawing
|  |  |  | X |  |  |  | Safety | Plan and Procedures | 4 | Plant Excavation Plans or Permits | 8DBF |  | Non-drawing
|  |  |  | X |  |  |  | Safety | Plan and Procedures | 4 | Safety Data Sheets | 4BD |  | Non-drawing
|  |  |  | X |  |  |  | Environmental | Plan and Procedures | 5 | Environmental permits | 12BF |  | Non-drawing
|  |  |  | X |  |  |  | Environmental | Plan and Procedures | 5 | Fugitive dust plan | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Environmental | Plan and Procedures | 5 | Hazardous material plan | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Environmental | Plan and Procedures | 5 | Scrap removal management plan and procedure | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Environmental | Plan and Procedures | 5 | Storm water management runoff / detention (pollution prevention) | 12AA plan / 12BF report |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Acceptance procedure | 8AA plan / 6BF record |  | Non-drawing
[8 empty] | QA / QC | Plan and Procedures | 6 | All performance guarantee test plans and procedures including correction curves | 8AA ? |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Cleaning, painting and packaging procedures | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Deviation records and approved deviation reports | 8AA plan / 10BF |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Inspection and non-destructive examination records | 8AA plan / 10D record |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Interior and exterior finish and color paint samples | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Manufacturer's data reports | 8AA plan / 10D record |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Material certifications, including filler metal certifications and test reporting | 8AA plan / 4BF record |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | NERC CIPS equipment specifications |  |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Non-destructive examination procedures and personnel qualifications | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Plan for handling, storage and pre-operational and operational maintenance of equipment | 8AA / 8BD record |  | Non-drawing
[8 empty] | QA / QC | Plan and Procedures | 6 | Pressure vessel requirements and certification plan | 8AA plan / 10D certification |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | QC inspection point program | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Special handling procedures for stainless steel or other sensitive materials | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Special process i.e., heat treating, plating, cladding, shot peening, etc. | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Test procedures as per ASME, ANSI, IEEE, API, HEI, NEMA, ASTM, etc. | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Test records plans to submit for owner review and acceptance | 8AA plan / 10D record |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Third party QA/QC analysis and reporting | 8AA plan |  | Non-drawing
|  |  |  | X |  |  |  | QA / QC | Plan and Procedures | 6 | Welding and qualification procedures | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Training | Plan and Procedures | 7 | Preliminary operations procedures (provided in Company format) |  |  | Non-drawing
|  |  |  | X |  |  |  | Training | Plan and Procedures | 7 | Training material | submit 9 months prior to anticipated mechanical completion date; allow 45 days to review |  | Non-drawing
|  |  |  | X |  |  |  | Training | Plan and Procedures | 7 | Written training program | 12B |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Access requirements | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Cable specification and codes |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Cable tray specifications and codes |  |  | Non-drawing
[8 empty] | Design | Data | 8 | Complete design calculations for all in-line flow | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Control system specification |  |  | Non-drawing
[8 empty] | Design | Data | 8 | Critical pipe stress analysis and support design | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | DCS graphics and logic design and implementation process plan | 8AA |  | Non-drawing
[8 empty] | Design | Data | 8 | Demolition plans of any existing equipment or structure to be removed |  |  | Non-drawing
[8 empty] | Design | Drawings | 8 | Demolition scope drawings (including markups of existing plant drawings) |  |  | Drawing
[8 empty] | Design | Data | 8 | Ductwork specification |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Electrical load list | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Equipment descriptions |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Erection information including lifting points, loads and storage requirements |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Fire suppression specification |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | General calculation approval | 4BP |  | Non-drawing
[8 empty] | Design | Data | 8 | Heat, material and power balance diagrams | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | HVAC specification |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Instrumentation specifications |  |  | Non-drawing
[8 empty] | Design | Data | 8 | Insulation specifications and codes |  |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Material lists including equivalent standard if different than those initially specified | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Overall design concept per tenant design considerations, concept, criteria and calculations | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | Design | Data | 8 | Overall performance data | 8AA |  | Non-drawing
[8 empty] | Design | Data | 8 | Pipe insulation specification |  |  | Non-drawing
[8 empty] | Design | Data | 8 | Pipe specification sheets to included material, installation and design criteria | 8AA |  | Non-drawing
[8 empty] | Design | Data | 8 | System descriptions including principle and mode of operation, required interlocks, hydraulic gradients, etc. | 8AA |  | Non-drawing
[8 empty] | Design | Data | 8 | System design requirements | 4AA |  | Non-drawing
[8 empty] | Design | Data | 8 | System flow and elementary diagrams-preliminary | 8AA |  | Non-drawing
[8 empty] | Design | Data | 8 | Valve design specifications |  |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Arc flash labels |  |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Arc flash study | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Aux power system analysis (SKM) | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Breaker coordination study | 2W |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | General survey | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Geotechnical investigation report | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Surveys | Studies | 9 | Noise study | 8AA |  | Non-drawing
[8 empty] | Surveys | Studies | 9 | Water balance | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | all certificates warranties and test reports |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | all maintenance instruction pm's with index per 1A. |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | all vendor manuals documentation with index per 1A. |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Anchor bolt / base pattern, mounting information, etc. |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Bill(s) of material listing (BOM) | 8BD |  | Non-drawing
[8 empty] | Equipment and Instrumentation | Documents | 10 | Cleaning and conservation procedures |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Description / design criteria (equipment and instrumentation data sheets as required with lists) | 4BP |  | Non-drawing
[8 empty] | Equipment and Instrumentation | Documents | 10 | Dismantling and assembly procedures for equipment with associated tests and checks prior to returning equipment to service (including the detailed assembly drawings) |  |  | Non-drawing
[8 empty] | Equipment and Instrumentation | Drawings | 10 | Drawing showing space needed for equipment maintenance and any fixed facilities such as trolley beams, etc. |  |  | Drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Effect of loss of normal power |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Equipment Alignment specification |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Equipment and material instruction bulletins and cut sheets |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Equipment start-up and commissioning plan | 6 months prior to start-up |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Erection information, including lifting points, loads, overall dimensions, etc. |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Final performance curves (include test data and test curves) |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Inspection and test data (to include shop test data) | 8BF |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Drawings | 10 | Installation instructions drawings and details |  |  | Drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Instrument vibration requirements and procedures |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | Issued as "as-installed" procedures (engineering, environmental, maintenance, operations, safety, etc.) (provided in Company format) with index per 1A. |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | Issued as "as-installed" project overview "turnover books" with index per 1A. |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | List of maintenance tools furnished with equipment |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Listing of any start-up prerequisites |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Lubrication schedule (showing initial fill levels, requirements and specifications for lubricants) | 4BD |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Manufacture's product sheet | 4BP |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Methods for trouble shooting |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Nameplate information and shop order numbers for each item of equipment and components |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Normal range of system variables |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Notice of shipment | 8BD |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Operating limits and hazards for all equipment and the system including alarm and trip set points for all devices |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Operating procedures and instructions for commissioning, startup, normal operation, shut downs, standby, emergency conditions and special safety precautions for individual items of equipment or system |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Operating, maintenance and installation instruction manuals and materials from manufacturer to include complete operations, troubleshooting and maintenance instruction | 6 months prior to start-up |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Drawings | 10 | Other vendor / manufacturer's drawings as appropriate with index per 1A. |  |  | Drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Performance warranty data |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Preventive maintenance schedule and maintenance instruction for equipment including standard and safety precautions | 6 months prior to start-up |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Protective coatings and preservatives | 4BD |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Receiving, handling and storage | 8BD |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | Reports: critical lift plan, engineering, EPA, geotechnical, final inspection, noise dosimetry, system turnover packages, etc. |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Setting and running clearances and tolerances |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Spare parts list (with OEM references, part numbers and pricing) | 6 months prior to start-up |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | Specifications |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Specifications | 4BP |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Testing and checking requirements |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Thermography specification |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Tolerance of electrical supply frequency variation |  |  | Non-drawing
|  |  |  | X |  |  |  | Project | Documents | 10 | Training documents / manuals |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Vendor specification sheets |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Vendor supplied certifications and inspections |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Vendor supplied data sheets |  |  | Non-drawing
|  |  |  | X |  |  |  | Equipment and Instrumentation | Documents | 10 | Vendor supplied test information |  |  | Non-drawing
|  |  |  | X |  |  |  | General Arrangement | Drawings | 11 | General arrangement drawings- Site Plan, Detail, Arrangement, Assembly drawings. | 4AA |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Elevation drawings | 8BF |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Floor plan interior layout and details | 4AA |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Foundation plan drawings | 8BF |  | Drawing
|  |  |  | X |  |  |  | Architectural | Documents | 12 | HVAC | 8BF |  | Non-drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | HVAC | 8BF |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Lighting and electrical plan | 8BF |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Plumbing and sanitary drain piping | 8BF |  | Drawing
|  |  |  | X |  |  |  | Architectural | Drawings | 12 | Siding and roofing details | 8BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | Aerial surveys | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | Construction site development including fences, gates, lay down and fabrication area, crane placement and temporary roads buildings and facilities, etc. | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Documents | 13 | Construction storm water management, drainage and sediment control plan | 4BF |  | Non-drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | Construction storm water management, drainage and sediment control plan | 4BF |  | Drawing
[8 empty] | Civil | Drawings | 13 | Pond / basin drawings | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | Sanitary and waste drain piping | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | site plan including paved and graveled roads, paved areas, parking, curbs, bollards, fences, gates and structures, etc. | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | site storm water management and drainage plan including underground storm water piping, catch basins, manholes and interconnects to existing piping systems | 4BF |  | Drawing
|  |  |  | X |  |  |  | Civil | Drawings | 13 | Survey, grading and contour plot locating structures and monuments referenced to plant and state plane coordinates | 4BF |  | Drawing
[8 empty] | Civil | Drawings | 13 | Underground oily and sanitary waste drain piping including interconnects to existing piping systems | 4BF |  | Drawing
[8 empty] | Civil | Drawings | 13 | Underground process piping and drains including interconnects to existing piping systems | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Elevated slabs | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Enclosure details roof, siding, insulation and framing, etc. |  |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Equipment foundations | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Foundation / support loading information | 2BF |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Foundation / support loading information | 2BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Foundation and substructure design and locations including caissons / piles and loadings | 4AA |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Foundation loading design calculations including dynamic analyses | 2BF |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Foundation loading design calculations including dynamic analyses | 2BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Ground floor slabs, sumps, trenches, trench covers, containments | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Paving and containment plans | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Paving and containment plans | 4AA |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Proposed building plans, elevations and interior layout | 4AA |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Rebar design, anchor bolts and patterns | 2BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Settlement records |  |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Settlement records |  |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Stair, platform and ladder location and design | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Structural loading design calculations including dynamic analyses | 2BF |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Structural loading design calculations including dynamic analyses | 2BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Structural steel design / fabrication and loading | 2BF |  | Drawing
[8 empty] | Structural | Drawings | 14 | Tank foundations and valve boxes | 4BF |  | Drawing
|  |  |  | X |  |  |  | Structural | Documents | 14 | Test reports and certifications | 1AC |  | Non-drawing
|  |  |  | X |  |  |  | Structural | Drawings | 14 | Test reports and certifications | 1AC |  | Drawing
[8 empty] | Structural | Drawings | 14 | Wall, pier and grade beams | 4BF |  | Drawing
[8 empty] | Mechanical | Documents | 15 | Conveyor systems |  |  | Non-drawing
[8 empty] | Mechanical | Drawings | 15 | Conveyor systems |  |  | Drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Ducting |  |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Drawings | 15 | Ducting |  |  | Drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Equipment data sheets to include type and technical requirements | 4BP |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Equipment lists to include tag ID | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Drawings | 15 | Fabrication and erection drawings |  |  | Drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Fabrication and erection support documentation |  |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Drawings | 15 | HVAC drawings |  |  | Drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Outline and arrangement of mechanical equipment including outline plan and elevation, dimensions, clearance requirements, terminal connector locations, sizes ratings, empty and full weights, etc. | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Drawings | 15 | Outline and arrangement of mechanical equipment including outline plan and elevation, dimensions, clearance requirements, terminal connector locations, sizes ratings, empty and full weights, etc. | 4AA |  | Drawing
|  |  |  | X |  |  |  | Mechanical | Documents | 15 | Specialty list including manufacture and model number (expansion joints, etc.) | 4AA |  | Non-drawing
|  |  |  | X |  |  |  | Mechanical | Drawings | 15 | Specialty list including manufacture and model number (expansion joints, etc.) | 4AA |  | Drawing
[8 empty] | Mechanical | Documents | 15 | Tanks and vessels |  |  | Non-drawing
[8 empty] | Mechanical | Drawings | 15 | Tanks and vessels |  |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Battery pack location drawing | WD |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Battery test reports | WD |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Cable insulation test reports | WD |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Cable list tabulation (Cable and circuit schedules) to included to and from, tag number, size, length, routing and schematic references | 4AA / monthly |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Cable list tabulation (cable and circuit schedules) to included to and from, tag number, size, length, routing and schematic references | 4AA / monthly |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Cable tray and conduit lists and routing (Cable tray and conduit schedule) |  |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Cable tray and conduit lists and routing (Cable tray and conduit schedule) |  |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Cable tray, tray hanger / support location and conduit routing | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Cable tray, tray hanger / support location and conduit routing | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Cathodic protection | 4BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Communications | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Communications | 8BP |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Duct bank and underground conduit | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Duct bank and underground conduit | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Electrical load list (total connected and total coincidental) | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Electrical load list (total connected and total coincidental) | 8BP |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Electrical schematics and logic, point-to-point wiring diagrams and interconnection diagrams between electrical / control components | 8BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Electrical trench and underground conduit plan |  |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Electrical trench and underground conduit plan |  |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Fiber and LAN connections | 4BF |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Fiber and LAN connections | 4BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Fiber optic cable tests | WD |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Grounding | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Grounding | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Hazard classification |  |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Hazard classification |  |  | Drawing
[8 empty] | Electrical | Documents | 16 | Heat tracing | 4BF |  | Non-drawing
[8 empty] | Electrical | Drawings | 16 | Heat tracing | 4BF |  | Drawing
[8 empty] | Electrical | Documents | 16 | Heat tracing schedule |  |  | Non-drawing
[8 empty] | Electrical | Drawings | 16 | Heat tracing schedule |  |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Internal schematics and point-to-point wiring diagrams of all panels, instrument racks and junction boxes | 8BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | ISO phase bus duct arrangement | 12AA |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | ISO phase bus duct arrangement | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Key diagrams for each bus (480v and above) | 8AA |  | Drawing
[8 empty] | Electrical | Drawings | 16 | Lighting and welding receptacle locations | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Lighting plan and area illumination levels | 4BP |  | Drawing
[8 empty] | Electrical | Documents | 16 | Motor data sheets | WD |  | Non-drawing
[8 empty] | Electrical | Drawings | 16 | Motor data sheets | WD |  | Drawing
[8 empty] | Electrical | Documents | 16 | Motor list with tag ID | 8BP |  | Non-drawing
[8 empty] | Electrical | Drawings | 16 | Motor list with tag ID | 8BP |  | Drawing
[8 empty] | Electrical | Documents | 16 | Motor speed-torque and acceleration time curves (250 hp and larger) | WD |  | Non-drawing
[8 empty] | Electrical | Drawings | 16 | Motor speed-torque and acceleration time curves (250 hp and larger) | WD |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Nameplate wording | 4BP |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Nameplate wording | 4BP |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Outline and arrangement drawings of electrical equipment including outline plan and elevation dimensions; physical arrangements including EEB internal layout; clearance requirements; terminal connection locations, sizes and ratings; empty and full weights, etc. | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Power system single line drawings | 8AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Power system three line drawings | 12AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Switchgear test reports | WD |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Switchgear, MCC nameplate drawings | 8BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Terminal block arrangements | 8BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Transformer outline and nameplate drawings | 8BF |  | Drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Transformer test reports | WD |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Documents | 16 | Unit Auxiliary Transformer (UAT) and Reserve Auxiliary Transformer (RAT) location | 8AA |  | Non-drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Unit Auxiliary Transformer (UAT) and Reserve Auxiliary Transformer (RAT) location | 8AA |  | Drawing
|  |  |  | X |  |  |  | Electrical | Drawings | 16 | Yard electrical plot plan |  |  | Drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Control logic diagrams | 16BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Control system architecture | 20BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Control system architecture | 20BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | DCS factory acceptance test (FAT) procedure | 4BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | DCS functional description including operating, indication and alarm philosophies, graphic screens and control and alarm set points | 16BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | DCS functional description including operating, indication and alarm philosophies, graphic screens and control and alarm set points | 16BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | DCS graphic displays | 12BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | DCS graphic displays | 12BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | DCS graphic layout sketches | 16BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | DCS graphic layout sketches | 16BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | DCS interface details | 20BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | DCS interface details | 20BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Input / output list (including set point and alarm) | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Input/output quantities (I/O list) | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Instrument / device / test port location | 8BF |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Instrument / device / test port location | 8BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Instrument data sheets including materials of construction, pressure and temperature ratings, range or calibration, set points, type of housing and mounting, power consumption, supplier, tag and documentation reference(s) | 8BP |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Instrument installation details | 8BF |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | Instrument list | 10BP |  | Non-drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Panel arrangements |  |  | Drawing
|  |  |  | X |  |  |  | I&C | Drawings | 17 | Physical location and layout drawings |  |  | Drawing
|  |  |  | X |  |  |  | I&C | Documents | 17 | PLC device list (programmable logic controller device list) |  |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Complete description of the insulation system including descriptions of the materials and attachment methods | 4BP |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Control valve data sheets | 4BP |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Heat tracing list | 4BP |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Inspection and test plan addressing all shop tests, examination and testing | 4BF |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Material certifications and test reports | 1AC |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Pipe insulation spec sheets |  |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Pipe line list (pipe schedule) with reference to material spec insulation spec and drawing references: P&ID and physical routing | 10AA |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Pipe material spec sheets | 10AA |  | Non-drawing
[8 empty] | Process Piping | Drawings | 18 | Pipe support details showing location, hot and cold loads and movements and bill of material | 4BP |  | Drawing
[8 empty] | Process Piping | Drawings | 18 | Piping & instrumentation diagrams | 10AA |  | Drawing
[8 empty] | Process Piping | Drawings | 18 | Piping isometrics (per line) | 4BP |  | Drawing
[8 empty] | Process Piping | Drawings | 18 | Piping physical drawings | 4BP |  | Drawing
[8 empty] | Process Piping | Documents | 18 | Piping specialty data sheets (i.e. flow element, orifice plate, etc.) | 4BP |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Piping specialty list | 10AA |  | Non-drawing
[8 empty] | Process Piping | Drawings | 18 | Process flow diagrams |  |  | Drawing
[8 empty] | Process Piping | Documents | 18 | Safety / relief valve data sheets | 4BP |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Test results | 1AC |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Valve list | 10AA |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Valve spec sheets | 10AA |  | Non-drawing
[8 empty] | Process Piping | Documents | 18 | Welding procedure specifications (WPS) and procedure qualification record (PQR) | 2BC |  | Non-drawing
|  |  |  | X |  |  |  | Project | Drawings | 19 | Drawing index per Attachment 1A. |  |  | Drawing
|  |  |  | X |  |  |  | Transmittal | Documents | 19 | Transmittals for documents |  |  | Non-drawing
|  |  |  | X |  |  |  | Transmittal | Drawings | 19 | Transmittals for drawings |  |  | Drawing
|  |  |  | X |  |  |  | Relay | Documents | 20 | Relay Specifications | 2AC |  | Non-drawing
|  |  |  | X |  |  |  | Relay | Documents | 20 | Relay setting orders | 2AC |  | Non-drawing
|  |  |  | X |  |  |  | Relay | Documents | 21 | As Built Documentation Checklist for Generator Interconnections | 2AC |  | Non-drawing
Note on E7: All project required documentation must be mark in this column.
Note on F7: Stages that these documents are expected to be provided to company project team.
Note on M7: Sample time schedules are provided here which should be cleared or modified by the project team based upon project needs and the schedule legend tab at the bottom of this workbook.
Note on N7: This column is provided so the contractor can submit their proposal for project time schedule.

## Submittal Schedule Legend
Legend for Documentation and Deliverables Punch List
#BP | Number # of weeks Before Procurement
Proc. | Procurement
#AA | Number # of weeks After Award
#BF | Number # of weeks Before Fabrication or before construction when no fabrication is required
#DBF | Number # of working Days Before Fabrication, or before construction if no fabrication is required
Fab. | Fabrication
Con. | Construction
#AC | Number # of weeks After Construction
#BD | Number # of weeks Before Delivery
WD | With Delivery
#B | Number # of weeks prior to performing task
#H | Number # of working Hours after completion of task
#D | Number # of working Days after completion of task
#W | Number # of working Weeks after completion of task
SPEC | See referenced specification section for additional requirements
CTS | Contractor to Supply
PTFP | Prior to Final Payment

## Revision History
Rev No. | Rev Date | Rev Description | Selection list for List tab
0 | 2013-03-05 | Ready for use | Submittal Disk entries
1 | 2013-04-04 | Added header information and new items to list | Drawing
2 | 2014-04-03 | Removed Auxiliary from Single & Three Line (Rows 230 & 231). Added row 264, (Process Flow Diagrams.) | Non-drawing
3 | 2014-07-02 | Added "Trench covers" & "Containments" to current line 192. Removed line 199 "Trench covers" and added current line 209, "Fabrication and erection drawings and supporting documentation".
4 | 2014-07-28 | Modified to contractual language
5 | 2014-09-09 | Modified Main Heading
6 | 2015-11-06 | Major changes
7 | 2015-12-31 | Merged original green area to rest of list.