## Sheet1
Customer Number | Resource Type | KW | Interconnection Date | Original Application Date | Interconnection Delay Explanation
61792 | Solar | 1900 | 2022-03-25 | 2017-09-01 | L3- This customer had 135 application submitted in 2017 and due to infrastructure requirements, completion of system being built was not complete until after 135 rate closure.
61793 | Solar | 356.4 | 2022-11-30 | 2017-05-15 | L3- This customer had 135 application submitted in 2018 and due to infrastructure requirements, completion of system being built was not complete until after 135 rate closure.
61794 | Solar | 868.32 | 2022-05-19 | 2020-08-05 | L3 - This customer had 136 application submitted in 2020 and due to infrastructure requirements, completion of system being built was not complete until after 136 rate closure.
61795 | Solar | 17.76 | 2022-05-23 | 2019-03-29 | Required accommodation to interconnect (transformer upgrade) This customer had 136 application submitted in 2019 and due to infrastructure requirements, completion of system being built was not complete until after 136 rate closure.
61796 | Solar | 186.96 | 2022-07-29 | 2020-02-10 | L2- This customer had 136 application submitted in 2020 and due to new construction and completion of system being built was not complete until after 136 rate closure.
61797 | Solar | 3.57 | 2022-08-11 | 2020-10-20 | extension given to complete project and put on schedule 136.
61798 | Solar | 88.39 | 2022-09-13 | 2020-07-17 | extension given to complete project due to manufacturing delays and put on schedule 136
61799 | Solar | 888.16 | 2022-09-21 | 2020-08-31 | L2- This customer had 136 application submitted in 2020 and due to new construction and completion of system being built was not complete until after 136 rate closure.
61800 | Solar | 3.84 | 2022-12-02 | 2020-09-24 | extension given to complete project and put on schedule 136
61801 | Solar | 5.44 | 2022-12-22 | 2020-08-19 | extension given to complete project due to original installer going out of business, we made exception to allow them to complete the project with new installer and put on schedule 136.