## Data Tables
Mitigation Program Category | Objective Items | 2020 Objectives (Goals) | 2020 Achievements (Actuals) | 2021 Objectives (Goals) | 2021 Achievements (Actuals) | 2022 Objectives (Goals) | 2022 Achievements (Actuals) | 2023 Objectives (Goals) | 2023 Achievements (Actuals) | 2024 Objectives (Goals) | 2024 Achievements (Actuals) | 2025 Objectives (Goals)
Risk Modeling & Drivers | Projects with Risk score assigned (EOY)
Risk Modeling & Drivers | Projects Completed:
Risk Modeling & Drivers | Median Risk Score of completed projects
Risk Modeling & Drivers | Median Risk Score of outstanding projects (EOY)
Risk Modeling & Drivers | Risk Score Range of outstanding projects (EOY)
Inspection & Correction Program | Distribution Visual Safety(miles): | [6 empty] | 17407 | 17422 | 37098
Inspection & Correction Program | Transmission Visual Safety (miles) | [6 empty] | 20888 | 20888 | 55868
Inspection & Correction Program | Distribution Detail: | [6 empty] | 1433 | 1433 | 1385
Inspection & Correction Program | Transmission Detail: | [6 empty] | 4149 | 4149 | 17879
Inspection & Correction Program | Distribution Intrusive: | [8 empty] | 5167
Inspection & Correction Program | Tansmission Intrusive: | [8 empty] | 5112
Inspection & Correction Program | Miles of Idle Transmission lines at End of Year (EOY)
Inspection & Correction Program | Miles of Idle Distribution lines at End of Year (EOY)
Inspection & Correction Program | Miles of IR Inspect on Trans lines: |  |  |  | 200 |  | 230 | 1638 | 1077 | 1638 | 1638
Inspection & Correction Program | Conditions Corrected in HFCA: |  | 2288 |  | 1824 |  | 2004 |  | 2732 |  | 6266
Vegetation Management | Distribution Line-Miles Inspected: |  | 1211 |  | 1209 |  | 1208 | 1198 | 1198 | 1172
Vegetation Management | Transmission Line-Miles Inspected: |  | 210 |  | 218 |  | 218 | 218 | 218 | 890
Vegetation Management | Total Line-Miles Inspected: | 0 | 1421 | 0 | 1427 | 0 | 1426 | 1416 | 1416 | 2062 | 0 | 0
Vegetation Management | Trees Trimmed/pruned: |  | 4746 |  | 12665 |  | 11723 |  | 7154 |  | 6439
Vegetation Management | Trees Removed (Included brush equiv): |  | 971 |  | 1942 |  | 1358 |  | 805 |  | 1109
Vegetation Management | Poles Radially Cleared: |  | 4712 |  | 5073 |  | 3144 |  | 4603 | 12529 | 12930
Environmental Program | Nests Managed: | [6 empty] | 52 | 105 |  | 76
Environmental Program | Poles Retrofitted: |  | 2866 |  | 2423 |  | 3966 | 3095 | 3429 |  | 4907
Environmental Program | Nestboxes maintained: |  |  |  |  | 5 |  |  | 500 |  | 500
System Hardening | Miles of Transmission Line - Undergrounding
System Hardening | Miles of Transmission Line - Covered Conductor
System Hardening | Miles of Transmission Line - Other
System Hardening | Total Miles of Transmission Line Rebuild Constructed: |  | 8 |  | 14.6 |  | 22.5 | 12 | 12 | 20 | 8 | 20
System Hardening | Miles of Distribution Line - Undergrounding
System Hardening | Miles of Distribution Line - Covered Conductor
System Hardening | Miles of Distribution Line - Other
System Hardening | Total Miles of Distribution Line Rebuild Constructed: | 0 | 0 | 0 | 0 | 0 | 43 | 37 | 37 | 80 | 94 | 60
System Hardening | Total Miles of Line Rebuild Constructed: | 0 | 8 | 0 | 14.6 | 82 | 65.5 | 49 | 49 | 100 | 102 | 80
System Hardening | Distribution Relays Upgraded: |  | 22 |  | 9 |  | 37 | 25 | 25 | 18 | 19 | 10
System Hardening | Transmission Relays Upgraded: | [5 empty] | 12 | 9 | 9 | 0 | 6
System Hardening | Recloser Replacements: | [6 empty] | 20 | 20 | 10 | 57 | 10
System Hardening | Total Relays and Reclosers Upgraded: | 0 | 22 | 0 | 9 | 0 | 49 | 89 | 54 | 28 | 82 | 20
System Hardening | Expulsion Fuses Replaced: |  | 417 |  | 990 |  | 1667 | 6000 | 1790 | 2000 | 2921 | 2000
System Hardening | Communicating Fault Indicators Installed: | [6 empty] | 1300 | 200 | 134 | 193
System Hardening | Weather Stations Installed: | [9 empty] | 25
System Hardening | Fire Mesh Wrap Installations: |  | 113
Situational Awareness Program | Weather Stations Installed: | 25 | 10 |  | 10 |  | 65 | 65 | 25 | 25 | 25 | 15
Situational Awareness Program | Weather Stations Maintenance Completed: | [5 empty] | 31 | 105 | 105 | 127 | 127
Situational Awareness Program | Weather Stations (End of Year Count) |  | 21 |  | 31 |  | 96
Situational Awareness Program | HPCC's Installed: |  |  |  | 1 |  |  | 1
Situational Awareness Program | Wildfire Detection Cameras Installed: | 14 |  |  | 14 |  | 0 | 5
Situational Awareness Program | Wildfire Detection Cameras Maintained:
System Operations | # Safety Settings Deployed: | [9 empty] | 1222
Field Operations & Work Practices | Emergency De-energizations: | [9 empty] | 24
Field Operations & Work Practices | COW Devices Purchased | [5 empty] | 1 | 1
Field Operations & Work Practices | Fire Vehicles Purchased:
Public Safety Power Shutoff (PSPS) Program | PSPS Events Conducted: | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0
Public Safety Power Shutoff (PSPS) Program | PSPS Watch Events where ECC was Activated: |  | 2 |  | 2 |  | 1
Public Safety Power Shutoff (PSPS) Program | Total Number of PSPS Shutoffs: | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Emergency Management Wildfire Response | Entities(cities, counties, agencies, etc) that participated in training events
Public Safety Partner Coordination Strategy | Tabletop Exercises Hosted: |  |  |  | 1 |  | 3 |  | 16 |  | 15
Public Safety Partner Coordination Strategy | Other Outreach and Training Events Conducted:
Public Safety Partner Coordination Strategy | Total Events Conducted: | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 16 | 0 | 15 | 0
Public Safety Partner Coordination Strategy | Total Public Safety Partner Individuals Trained:
Wildfire Safety & Preparedness Engagement Strategy | Community Webinars Conducted: | [7 empty] | 1 |  | 1
Wildfire Safety & Preparedness Engagement Strategy | Community Members Trained:
Wildfire Safety & Preparedness Engagement Strategy | Total Wildfire Safety and Preparedness Engagement Events: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Industry Collaboration | Number of Associations currently collaborating with: |  | 6 |  | 6 |  | 7
Plan Monitoring & Implementation | Equipment and Assets lost - HFCA Areas
Plan Monitoring & Implementation | Equipment and Assets lost - Non-HFCA Areas
Other Elements to include:
| Enhanced Safety Settings - Event Count | [9 empty] | 1222
| Emegency De-energization - Event Count | [9 empty] | 24
Note on B2: ====== ID#AAABm5O_nwc Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B3: ====== ID#AAABm5O_nwM Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B4: ====== ID#AAABm5O_nws Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B5: ====== ID#AAABm5O_nxQ Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B6: ====== ID#AAABm5O_nwQ Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B13: ====== ID#AAABm5O_nws Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B14: ====== ID#AAABm5O_nws Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B26: ====== ID#AAABm5O_nxA Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B27: ====== ID#AAABm5O_nxU Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B28: ====== ID#AAABm5O_nxI Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B29: ====== ID#AAABm5O_nwY Jeremy Hirschi (2025-07-03 18:16:18) This is a aggregated total of the above subprojects
Note on B30: ====== ID#AAABm5O_nww Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B31: ====== ID#AAABm5O_nxE Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B32: ====== ID#AAABm5O_nxM Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B45: Please provide end of year counts for each corresponding year) ======
Note on B46: ====== ID#AAABm5O_nwE Jeremy Hirschi (2025-07-03 18:16:18) HPCC = "High Performance Computing clusters"
Note on B48: ====== ID#AAABm5O_nwg Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B52: ====== ID#AAABm5O_nw0 Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B60: ====== ID#AAABm5O_nxk Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B62: ====== ID#AAABm5O_nxc Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B65: ====== ID#AAABm5O_nwU Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.
Note on B66: ====== ID#AAABm5O_nxY Jeremy Hirschi (2025-07-03 18:16:18) This is a new data point requested. Please report current year and all other years.

## Costs Data Tables
Mitigation Program Category |  | Objective Items ($ Millions) | 2020 Plan (Approved) | 2020 Actuals | 2021 (Approved) | 2021 Actuals | 2022 (Approved) | 2022 Actuals | 2023 (Approved) | 2023 Actuals | 2024 (Approved) | 2024 Actuals | 2025 (Approved)
Risk Modeling & Drivers | Capital Spend | Distribution Costs | 3.25 | 4.1 | 3 | 2.7 | 2.5 | 3 | 0.955 | 2.3 | 0 | 2.4 | 0.6
Risk Modeling & Drivers | Capital Spend | Transmission Costs |  |  |  |  | 0.5 | 0.8 |  |  | 0 | 0 | 0
Risk Modeling & Drivers | O&M Spend | Distribution Costs | 0 | 0 | 0.2 | 0.1 | 0.2 | 0.1 |  | 1.5 | 0 | 3.1 | 0
Risk Modeling & Drivers | O&M Spend | Transmission Costs |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Inspection & Correction Program | Capital Spend | Distribution Costs | 1 | 2.2 | 1.5 | 4.8 | 4.5 | 11 | 1.5 | 13.8 | 1.5 | 18.5 | 20
Inspection & Correction Program | Capital Spend | Transmission Costs |  |  |  |  | 0.2 | 0.2 |  | 0 | 0 | 1.1 | 0
Inspection & Correction Program | O&M Spend | Distribution Costs | 3.2 | 2.6 | 1.86 | 1.3 | 1.9 | 4.9 |  | 7.5 | 1.9 | 3.3 | 13.5
Inspection & Correction Program | O&M Spend | Transmission Costs | 0.8 | 0.7 | 0.2 | 0.8 | 0.2 | 0.4 |  | 0.4 | 0.2 | 0.9 | 1
Vegetation Management | O&M Spend | Distribution Costs | 1.5 | 0 | 1.3 | 2.8 | 1.3 | 2.7 | 1.3 | 2 | 1.3 | 3.1 | 3.6
Vegetation Management | O&M Spend | Transmission Costs | 0.3 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3
Environmental Program | Capital Spend | Distribution Costs | 0.2 | 0 | 0.2 | 0.05 | 0.2 | 0.6 | 0.2 | 1.4 | 0.2 | 0.4 | 0.5
Environmental Program | Capital Spend | Transmission Costs |  | 0 |  |  | 0 | 0 | 0.1 | 0 | 0 | 0 | 0
Environmental Program | O&M Spend | Distribution Costs | 0.1 | 0.03 | 0.4 | 0.25 | 0.4 | 0.3 | 0.4 | 0.3 | 0.4 | 0.1 | 0.5
Environmental Program | O&M Spend | Transmission Costs | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 |  | 0.1 | 0 | 0
System Hardening | Capital Spend | Transmission Line - Undergrounding
System Hardening | Capital Spend | Transmission Line - Covered Conductor
System Hardening | Capital Spend | Transmission Line - Other
System Hardening | Capital Spend | Total Transmission Line Rebuild: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Hardening | Capital Spend | Distribution Line - Undergrounding
System Hardening | Capital Spend | Distribution Line - Covered Conductor
System Hardening | Capital Spend | Distribution Line - Other
System Hardening | Capital Spend | Total Distribution Line Rebuild: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Hardening | Capital Spend | Total Line Rebuild Constructed: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Hardening | Capital Spend | Distribution Costs | 29.6 | 10 | 44.7 | 8 | 41.6 | 37.1 | 37.7 | 53.7 | 20.9 | 128.9 | 85
System Hardening | Capital Spend | Transmission Costs |  | 5.8 |  | 4.7 | 20 | 20.6 |  | 23.3 | 5.9 | 24.7 | 50
System Hardening | O&M Spend | Distribution Costs | 0 | 0 | 0.17 | 0.1 | 0.2 | 0 |  | 0.2 | 0.1 | 0.5 | 0
System Hardening | O&M Spend | Transmission Costs | 0 | 0.3 | 0 | 0.1 | 0 | 0.1 |  | 0.4 | 0 | 0 | 0
Situational Awareness Program | Capital Spend | Distribution Costs | 0.445 | 1.4 | 0.24 | 2 | 1.5 | 3.8 | 0 | 5.6 | 0 | 1.7 | 0.3
Situational Awareness Program | Capital Spend | Transmission Costs |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
Situational Awareness Program | O&M Spend | Distribution Costs | 0.3 | 0.2 | 0.4 | 0.36 | 0.4 | 3.7 |  | 2.6 | 0.5 | 3.9 | 0.7
Situational Awareness Program | O&M Spend | Transmission Costs |  | 0 | 0 | 0.08 | 0 | 0
System Operations |  | # Safety Settings Deployed:
Field Operations & Work Practices | Capital Spend | Distribution Costs |  |  |  |  | 0 | 1.2 |  | 5.8 | 0 | 0.5 | 0.5
Field Operations & Work Practices | Capital Spend | Transmission Costs |  |  |  |  | 0 | 0
Field Operations & Work Practices | O&M Spend | Distribution Costs | [7 empty] | 2.3 | 0 | 1.7 | 0
Field Operations & Work Practices | O&M Spend | Transmission Costs | [7 empty] | 0.1 | 0 | 0.8 | 0.6
Public Safety Power Shutoff (PSPS) Program | Capital Spend | Distribution Costs
Public Safety Power Shutoff (PSPS) Program | Capital Spend | Transmission Costs
Public Safety Power Shutoff (PSPS) Program | O&M Spend | Distribution Costs | [7 empty] | 0 | 0 | 0 | 8.2
Public Safety Power Shutoff (PSPS) Program | O&M Spend | Transmission Costs | [8 empty] | 0 | 0 | 0
Emergency Management Wildfire Response | O&M Spend | Distribution Costs
Emergency Management Wildfire Response | O&M Spend | Transmission Costs
Public Safety Partner Coordination Strategy | Capital Spend | Distribution Costs | [7 empty] | 1.9 | 0 | 0 | 0
Public Safety Partner Coordination Strategy | Capital Spend | Transmission Costs | [8 empty] | 0 | 0 | 0
Public Safety Partner Coordination Strategy | O&M Spend | Distribution Costs | [7 empty] | 0.1 | 0 | 0.1 | 0
Public Safety Partner Coordination Strategy | O&M Spend | Transmission Costs
Wildfire Safety & Preparedness Engagement Strategy | Capital Spend | Distribution Costs
Wildfire Safety & Preparedness Engagement Strategy | Capital Spend | Transmission Costs
Wildfire Safety & Preparedness Engagement Strategy | O&M Spend | Distribution Costs | [8 empty] | 0 | 0.1 | 0
Wildfire Safety & Preparedness Engagement Strategy | O&M Spend | Transmission Costs
Industry Collaboration | Capital Spend | Distribution Costs
Industry Collaboration | Capital Spend | Transmission Costs
Industry Collaboration | O&M Spend | Distribution Costs | [8 empty] | 0 | 0.1 | 0
Industry Collaboration | O&M Spend | Transmission Costs | [8 empty] | 0 | 0 | 0
Plan Monitoring & Implementation | Capital Spend | Distribution Costs | [8 empty] | 0 | 0 | 0
Plan Monitoring & Implementation | Capital Spend | Transmission Costs | [8 empty] | 0 | 0 | 0
Plan Monitoring & Implementation | O&M Spend | Distribution Costs | [8 empty] | 0 | 0.7 | 0
Plan Monitoring & Implementation | O&M Spend | Transmission Costs | [8 empty] | 0 | 0 | 0
Other Elements to include:
|  | Enhanced Safety Settings - Event Count | [9 empty] | 1222
|  | Emegency De-energization - Event Count | [9 empty] | 24

## Reports Provided by RMP
Mitigation Program Category | 2020-2022 Achievements (Actuals) | 2023 Objectives (Goals) | 2023 Achievements (Actuals) | 2024 Objectives (Goals) | 2024 Achievements (Actuals) | 2025 Objectives (Goals)
Risk Modeling & Drivers | Maintained FHCA maps and risk assessment. Initial procurement of new risk modeling tools, datasets, and software. | Refresh the FHCA Map. Utilize WRRM to model utility asset fire risk. Implement advanced data analytics tool. | Completed development for combined composite risk score. Completed FHCA MAP update. | Review and Update Composite Risk Score. | Reviewed new FireSight model outputs to update risk scores. Participated in joint utility workshops, conferences, and benchmarking discussions to evaluate industry practices for wildfire risk modeling and analysis. | Continue to update risk scores based on new model outputs and benchmarking.
Inspection & Correction Program | Completed inspections of all poles in the FHCA. Corrected 2,004 fire threats. 200 miles of IR inspection completed. | Continuation of incremental FHCA inspection programs on 656 line-miles of overhead conductors and relevant portions of the service territory (18,151 line-miles). Expand the enhanced IR inspection program to include a total of 1,638 interconnected transmission lines with the FHCA. | Completed standard inspection programs: Distribution Visual Safety: 17,407; Transmission Visual Safety: 20,888; Distribution Detail: 1,433; Transmission Detail: 4,149. Completed 1,077 miles of transmission IR inspections (out of 1,638 planned). Corrected 2,732 conditions in FHCA. | Continue standard inspection programs: Distribution Visual Safety: 37,098; Transmission Visual Safety: 55,868; Distribution Detail: 1,385; Transmission Detail: 17,879; Distribution Intrusive: 5,167; Transmission Intrusive: 5,112. Perform infrared inspection on 1,638 miles of transmission lines. | Completed all listed standard inspection programs (numbers met). Completed 1,638 miles of transmission IR inspections. Corrected 6,266 conditions in FHCA. | Continue standard inspection programs and IR inspections at planned levels.
Vegetation Management | Inspected over 1,427 line-miles. Trimmed over 24,388 trees. Removed over 3,300 trees (including brush equivalent). Radially cleared over 8,217 poles. | Continue FHCA vegetation management programs including expanded post-work clearances (Annual inspections, Tree trimming, Tree removal, Radial clearing). | Performed FHCA vegetation inspections and corrections: Distribution Miles: 1,198; Transmission Miles: 218. Program resulted in 805 trees removed, 7,154 trees pruned, and 4,603 poles cleared. | Perform FHCA vegetation inspections and corrections: Distribution Miles: 1,172; Transmission Miles: 890; Pole count: 12,529. | Performed FHCA vegetation inspections and corrections (all listed numbers met). Program resulted in 1,109 trees removed, 6,439 trees pruned, and 12,930 poles cleared. | Continue FHCA vegetation management including inspections, trimming, removal, and pole clearing.
Environmental Program | N/A (Specific quantifiable achievements for 2020-2022 not explicitly listed in summary table). | Manage 52 nests and retrofit 3,095 poles. Complete project scoping for habitat improvements. | Completed environmental work that resulted in 105 nests managed, 3,429 poles retrofitted, and 500 nest boxes maintained for cavity nesting birds. Completed project scoping with Pheasants Forever for habitat improvements to be completed in 2024. | Continued avian protection plan work, complete habitat project scoping and planning with partners for 2025 work. | Nests Managed: 76. Poles Retrofitted: 4,907. Nest Boxes: 500. Habitat project scoping and planning/budgeting completed for a collaborative project with the U.S. Forest Service in Southern Utah, with work scheduled for 2025. | On-the-ground vegetation and habitat work scheduled to begin in 2025.
System Hardening | 65 miles of line rebuild constructed. 55 relays and reclosers upgraded. 2,936 expulsion fuses replaced. 1,598 communicating fault indicators installed. | Design and construct 220 miles of line rebuild projects. Upgrade 89 relays and reclosers. Replace 6,000 expulsion fuses. Install 1,300 communicating fault indicators. | Completion of 49 miles of Line rebuild (12 transmission line miles, 37 distribution line miles). Completion of 54 device upgrades (25 distribution relays, 9 transmission relays, 20 recloser replacements). Completion of 1,790 expulsion fuses replaced. 200 CFCI installed as replacements. | Complete line rebuild projects: 20 miles of transmission lines, 80 miles of distribution lines. Complete Device Upgrades: 18 distribution relays, 0 transmission relays, 10 recloser replacement. Complete 2,000 expulsion fuse replacements. Complete 134 CFCI replacements. | Completion of 102 miles of Line rebuild (8 transmission line miles, 94 distribution line miles). Completion of 82 device upgrades (19 distribution relays, 6 transmission relays, 57 recloser installations). Completion of 2,921 expulsion fuses replaced. 193 CFCI installed as replacements. 25 Weather Station Installations completed (target met). Total Weather Stations Fleet: 151 (target met). | Continue line rebuilds (e.g., 60 dist./20 trans. miles from original 2023 plan), device upgrades (e.g., 10 dist. relays/10 reclosers from original 2023 plan), fuse replacements (e.g., 2,000 from original 2023 plan), CFCI installations.
Situational Awareness Program | Installed 95 weather stations. Implemented FPI. Procured and installed 1 HPCC for operational forecasting. Installed 14 wildfire detection cameras. | Install 65 additional weather stations. Implement WRF ensembles. Procure additional HPCCs for operational forecasting. Install 5 wildfire cameras. Improve the public weather awareness website. | Meteorology's department continued weather modeling. Completed installations of 25 additional weather stations. Completed maintenance on 105 weather stations. Continued use of WFA-E modeling. Completed the development of the Modified Hot-Dry-Windy Index mHDWI. | Continued weather modeling by meteorology department. Expand weather station network with 25 additional weather stations. Complete annual weather station maintenance on 127 weather stations. Continue use of weather modeling tools. Continue daily district fire risk assessments. | Completed all listed activities, confirming numbers met for weather stations. | Continue weather modeling, station network expansion (15 additional planned), maintenance, tool use, and daily risk assessments.
System Operations | Risk-based implementation of EFR settings and re-energization practices. | Continue risk-based implementation of EFR settings and re-energization practices. | The use of enhanced safety settings were utilized in 2023. | Continue deployment of enhanced safety settings. | Completed - enhanced safety settings were utilized in 2024. | Continue deployment of enhanced safety settings.
Field Operations & Work Practices | Risk-based work practices. Additional local assessments to inform situational awareness. Purchased 1 COW device. | Continue implementation of risk-based work practices. Assess additional equipment needs. Develop and release interactive training apps and eBooks for internal wildfire preparedness. | Purchased 6 Starlink Satellite communication devices. Completed purchases of fire trucks, backhoes, forklifts, UTV's, and equipment trailers. Development began on wildfire training eBooks and Applications for delivery in 2024. | Procure additional communication equipment to aid in field response. Procure vehicles to aid in wildfire mitigation. Develop wildfire eBooks and training applications. | Procured 26 Starlink satellite communication devices. Procured one additional fire truck and 17 other related upfits/fees. Completed development of training materials including eBooks and mobile applications. | Continue procuring equipment and developing training materials.
Public Safety Power Shutoff (PSPS) Program | ECC activated for 2 PSPS watch events in 2021. Conducted 1 PSPS event in 2022. Stood up 1 CRC during the 2022 PSPS event. | Broaden public outreach and engagement on PSPS and wildfire safety. Strategize CRC locations with public safety partners. Streamline GIS and information sources (PSP Portal). Continue development of internal communication and coordination tools. | Completed PSPS readiness and no PSPS events were required in 2023. | Continue PSPS Readiness. | Completed PSPS readiness and no PSPS events were required in 2024. | Continue PSPS readiness.
Emergency Management Wildfire Response | N/A (Not explicitly listed in 2023 WMP summary for 2020-2022 achievements). | Continue wildfire response readiness. | Completed and the Company's emergency response is guided by NIMS. | Continue wildfire response readiness. | Completed. The Company's emergency response is guided by NIMS. | Continue wildfire response readiness.
Public Safety Partner Coordination Strategy | Hosted 13 tabletop exercises in 2022. | Full implementation of PSP Portal. Continue hosting tabletop exercises and assessing PSP interest in other preparedness strategies (functional exercises, workshops, etc.). | Completed 16 events with public safety partners. In 2023 the development began for Public Safety Partner Portal and is on track for delivery in 2024. | Complete events with public safety partners for emergency response. Implement improvements to the Public Safety Partner Portal. | Completed 15 events with public safety partners. The Public Safety Partner Portal was completed in 2024. The Company is conducting outreach and training in 2025. | Conduct outreach and training on the PSP Portal.
Wildfire Safety & Preparedness Engagement Strategy | Conducted a multi-pronged outreach campaign. Launched updated webpages to improve customer experience and accessibility. Introduced new infographics to show wildfire mitigation work in progress. | Continue multi-pronged outreach campaign. Continue to refine information for ease of use and access. Identify community engagement opportunities with external stakeholders. | Translated the website into Spanish and conducted 1 community webinar. | Continue community outreach about wildfire safety. | Conducted 1 community webinar (in April 2024). | Continue community outreach and refinement of information.
Industry Collaboration | Participated in the IWRMC. Climate READi to develop a common approach across utilities in relation to climate data and grid hardening technologies. | Leverage lessons learned from the IWRMC. | Continued membership with the IWRMC. Rocky Mountain Power began participating in a three-year study referenced as Climate READI. | Continue industry collaboration involvement. Participated in climate risk initiative. | Continued active engagement in industry collaborations. Participated in a three-year Electric Power Research Institute Climate Resilience and Adaptation Initiative (READI). | Continue industry collaboration and Climate READI participation.
Plan Monitoring & Implementation | Developed a centralized repository of WMP related documentation. | Continue research into new technologies, equipment, and strategies that aid in wildfire mitigation. Review QA/QC processes for program tracking. | The team responsible developed the WMP and is actively tracking initiatives. | Continue to develop the WMP and ensure adherence to Plan. | Filed the updated 2023 Utah WMP and ensured each initiative progressed toward the established plan. | Continue WMP development, adherence, and research.