## 1 of 1
2022 Infrastructure Replacement Budget
For the Third Quarter Ending September 30, 2022
| A | B | C | D
| Feeder Line | 2022 Budget | Actual Costs as of September 30, 2022 | Variance (Over) / Under
High Pressure
1 | FL43 | 16145000 | 9128282.01 | 7016717.99 | 1/
2 | FL13 | 33200240 | 40916021.05 | -7715781.05 | 2/
3 | FL12/FL33 | 17467285 | 8331793.04 | 9135491.96 | 3/
4 | Other | 0 | 956703.95 | -956703.95 | 4/
5 | Total High Pressure | 66812525 | 59332800.05 | 7479724.95
Intermediate High Pressure
6 | Salt Lake County Total | 10000000 | 7594900.31 | 2405099.69
7 | Total Intermediate High Pressure | 10000000 | 7594900.31 | 2405099.69
8 | Pre-engineering (Future Projects) | 550000 | 410964.45 | 139035.55
9 | Total | 77362525 | 67338664.81 | 10023860.19
1/ | FL43 will be replaced by FL134. Construction on this project has paused pending the resolution of an ongoing property dispute.
2/ | Cost escalation on material, labor, consumables and construction delays continue to exceed the estimated costs of the FL13 project.
3/ | The Company's original budget showed FL33 and FL12 on separate rows, but engineering and system configuration have decided that the portion of FL33 replaced this year will be renamed FL12. As such, the FL12 and FL33 rows have been combined to align with the Company's treatment of this year's FL12 and FL33 replacement as one project and one new resulting feederline (FL12).
4/ | Due to a variety of factors, more work is able to be completed in 2022 than originally budgeted for FL42, FL47, and FL19. The work is expected to total approximately $1.2 million cumulatively for these projects for 2022.