## 1 of 1
2022 Infrastructure Replacement Budget
For the Fourth Quarter Ending December 31, 2022
| A | B | C | D
| Feeder Line | 2022 Budget | Actual Costs as of December 31, 2022 | Variance (Over) / Under
High Pressure
1 | FL43 | 16145000 | 9889553.51 | 6255446.49 | 1/
2 | FL13 | 33200240 | 47066181.01 | -13865941.01 | 2/
3 | FL12/FL33 | 17467285 | 15728116.14 | 1739168.86 | 3/
4 | Other | 0 | 3107131.92 | -3107131.92 | 4/
5 | Total High Pressure | 66812525 | 75790982.58 | -8978457.58
Intermediate High Pressure
6 | Salt Lake County Total | 10000000 | 8686723.7 | 1313276.3
7 | Total Intermediate High Pressure | 10000000 | 8686723.7 | 1313276.3
8 | Pre-engineering (Future Projects) | 550000 | 633822.61 | -83822.61
9 | Total | 77362525 | 85111528.89 | -7749003.89
1/ | FL43 has been renamed FL134. Construction on this project has paused pending the resolution of an ongoing property dispute.
2/ | The cost of material and labor have escalated, and construction delays have also increased the costs, resulting in expected costs exceeding the original estimated costs for FL13.
3/ | The Company's original budget showed FL33 and FL12 on separate rows, but the Company's engineering and system configuration departments have determined that the portion of FL33 replaced this year will be renamed FL12. As such, the FL12 and FL33 rows have been combined to align with the Company's treatment of this year's FL12 and FL33 replacement as one project and one new resulting feederline (FL12).
4/ | The Company invested approximately $1.2 million to replace portions of FL42, FL47, and FL19, while completing work on separate but connected infrastructure. In addition, the Company spent $1.9 million on materials and property rights for FL34 and FL 022 /23 in anticipation of replacing those lines in 2023.