## Sheet1
Filing | Due Date | Division Action | Opportunity for Interested Party Comments | Action Requested of PSC
Replacement Infrastructure Tracker Annual Plan and Budget | 2022-11-15 | Division Review and Action Request Response | Parties can file comments consistent with PSC notice | Acknowledge plan and budget
1st Quarter Tracker Variance Report | 2023-06-30 | Division Review
Replacement Infrastructure Tracker Technical Conference | 2023-06-30 | No action | Parties can attend public portion of Tech Conf and confidential portion subject to meeting confidentiality requirements | Schedules tech conference
Replacement Infrastructure Tracker Master List Update | 2023-06-30 | Division Review
2nd Quarter Tracker Variance Report | 2023-09-30 | Division Review
Replacement Infrastructure Tracker Rate Adjustment Filing 1 | At least once annually. Anticipated in August 2023. | Division Review and Filed Comments | Parties can raise concerns, but short turnaround for interim rates | Approve interim rates; final prudency review of the plan (i.e. which lines to replace and when); prudency of how DEU carried out the plan (i.e. accuracy of costs, prudency in carrying out construction) not yet final.
3rd Quarter Tracker Variance Report | 2023-12-31 | Division Review
Replacement Infrastructure Tracker Rate Adjustment Filing 2 | At least once annually. Anticipated in October 2023. | Division Review and Filed Comments | Parties can raise concerns, but short turnaround for interim rates | Approve interim rates
4th Quarter Tracker Variance Report | 2024-03-31 | Division Review
Multi Year Accounting Audit | Before filing of General Rate Case | Division Report to Commission. Division completes audit, determines final prudency of plan but reserves the right for out of cycle period adjustments or changes until next general rate case. | Parties can file comments on the final prudency of plan but have the right for out of cycle period adjustments or changes until next general rate case. | Commission to establish a comment period and consider any additional process and determines final prudency of plan based on parties recommendations.
General Rate Case | 2025-05-02 | Division raises any final issues before resources are in base rates | Parties can challenge prudency of how the Company carried out the plan (i.e. accuracy of costs, prudency in carrying out construction). | Final approval of prudency of accuracy of costs (i.e. accuracy of costs, prudency in carrying out construction).
Additional Notes:
DEU will include an updated version of this schedule in its Annual Plan and Budget through the remaining life of the ITP
DEU will include in its procedural background of the rate adjustment filings, a listing of the dockets which have addressed the projects included in the updated rates